## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | Complexity | BE | FE | Status | Update Details
1 | Sign Up | Authentication & Authorization | All Users | User registration with role selection (Admin, Moderator, DataProvider, DataConsumer). Includes email validation and password strength requirements. | Simple |  |  | Done | Implemented with JWT token generation and role-based access control
2 | Login | Authentication & Authorization | All Users | Login with email and password. Supports 4 roles: Admin, Moderator, DataProvider, DataConsumer. Returns JWT token with 24h expiry. | Simple |  |  | Done | JWT authentication with role-based redirect after login
3 | Logout | Authentication & Authorization | All Users | Logout functionality that clears JWT token from localStorage and redirects to home page. | Simple |  |  | Done | Token removal and session cleanup
4 | Home / Catalog | Browse & Search Dataset | Data Consumer | Public catalog page displaying all approved datasets. Features: search by name/description, filter by category, pagination, dataset cards with preview info. | Medium |  |  | Done | Integrated with GET /api/datasets endpoint, responsive design with TailwindCSS
5 | Dataset Detail | Browse & Search Dataset | Data Consumer | Detailed view of a dataset showing: description, provider info, data preview, pricing info, purchase options (3 package types). | Medium |  |  | Done | Shows dataset metadata and purchase options for Data/Subscription/API packages
6 | Search & Filter | Browse & Search Dataset | Data Consumer | Search functionality by dataset name/description/provider. Filter by category, province, date range. Real-time search results. | Medium |  |  | Done | Client-side filtering with API integration
7 | Data Package Preview | Purchase & Manage | Data Consumer | Preview data before purchase: select province, district, date range. Shows row count, estimated price, sample data preview. | Medium |  |  | Done | GET /api/data-packages/preview endpoint with location and date filtering
8 | Data Package Purchase | Purchase & Manage | Data Consumer | Purchase data package by location (province/district) and date range. Creates purchase record, calculates price based on row count (10 VND/row). | Medium |  |  | Done | POST /api/data-packages/purchase with automatic price calculation
9 | Data Package Download | Purchase & Manage | Data Consumer | Download purchased data package as merged CSV from all providers matching location and date criteria. Includes all 17 fields per record. | Medium |  |  | Done | GET /api/data-packages/{id}/download merges data from multiple providers
10 | Subscription Package Purchase | Purchase & Manage | Data Consumer | Subscribe to real-time dashboard for a province. Select province and duration (months). Monthly fee: 500,000 VND. Provides dashboard access. | Medium |  |  | Done | POST /api/subscription-packages/purchase with duration selection
11 | Subscription Dashboard | Purchase & Manage | Data Consumer | Real-time analytics dashboard for subscribed province. Charts: energy over time, station distribution, peak hours. Aggregates data from all providers. | Complex |  |  | Done | Dashboard with 3 chart endpoints, Recharts integration, real-time data aggregation
12 | Cancel Subscription | Purchase & Manage | Data Consumer | Cancel active subscription. Stops access to dashboard and prevents future charges. | Simple |  |  | Done | POST /api/subscription-packages/{id}/cancel endpoint
13 | API Package Purchase | Purchase & Manage | Data Consumer | Purchase API call credits. Select number of API calls (100 VND/call). Provides programmatic access to EV charging data. | Medium |  |  | Done | POST /api/api-packages/purchase with credit selection
14 | Generate API Key | Purchase & Manage | Data Consumer | Generate API key for purchased API package. Format: evdata_xxxxx. Key used for authentication in API requests. | Simple |  |  | Done | POST /api/api-packages/{id}/generate-key with key validation
15 | API Key Management | Purchase & Manage | Data Consumer | View all API keys for purchased packages. Revoke keys, view usage statistics (calls used vs total). | Medium |  |  | Done | GET /api/api-packages/{id}/keys and revoke functionality
16 | Public API Endpoint | Purchase & Manage | Data Consumer | Public REST API endpoint: GET /api/data?provinceId=X&districtId=Y&startDate=...&endDate=... Requires X-API-Key header. Returns JSON data. | Complex |  |  | Done | API endpoint with key validation, rate limiting, and query parameters
17 | Checkout Page | Purchase & Manage | Data Consumer | Checkout page showing purchase summary, total price, payment method selection. Redirects to PayOS payment gateway. | Medium |  |  | Done | Payment creation with PayOS integration, redirect to checkout URL
18 | Payment Callback | Purchase & Manage | Data Consumer | PayOS payment callback handler. Validates payment status, activates purchase, creates revenue shares, redirects to success/failure page. | Complex |  |  | Done | GET /api/payments/callback with webhook signature validation
19 | Payment Success/Failure | Purchase & Manage | Data Consumer | Payment result pages showing success or failure message. Success page provides download/access links for purchased packages. | Simple |  |  | Done | PaymentSuccess and PaymentFailed components with purchase activation status
20 | My Purchases | Purchase & Manage | Data Consumer | List all purchases (Data Packages, Subscriptions, API Packages). Shows status, purchase date, download/access links. Filter by type. | Medium |  |  | Done | GET /api/purchases/my-purchases aggregates all purchase types
21 | Upload Dataset | Dataset Management | Data Provider | Upload CSV dataset with metadata. Download CSV template first. File validation, parsing, storing records in database. Status: Pending moderation. | Complex |  |  | Done | POST /api/datasets with CSV parsing, template validation, DatasetRecord creation
22 | Download CSV Template | Dataset Management | Data Provider | Download CSV template with headers and sample data. Template includes all 17 required fields: StationId, StationName, ProvinceId, DistrictId, ChargingTimestamp, EnergyKwh, etc. | Simple |  |  | Done | GET /api/datasets/template returns CSV with sample data
23 | My Datasets | Dataset Management | Data Provider | View all uploaded datasets. Shows status (Pending/Approved/Rejected), upload date, record count, moderation history. | Medium |  |  | Done | GET /api/datasets/my-datasets filtered by provider
24 | Provider Dashboard | Dataset Management | Data Provider | Provider dashboard showing: total datasets, earnings summary, revenue chart, recent activities, pending payouts. | Medium |  |  | Done | Dashboard with earnings API integration, revenue visualization
25 | Moderation List | Moderation | Moderator/Admin | List all datasets pending moderation. Shows dataset info, provider, upload date, record count. Filter by status. | Medium |  |  | Done | GET /api/moderation/pending with pagination
26 | Preview Dataset Data | Moderation | Moderator/Admin | Preview paginated dataset records for quality check. Shows sample data in table format. Pagination: 50 records per page. | Medium |  |  | Done | GET /api/moderation/{id}/preview-data with pagination
27 | Download Dataset for Review | Moderation | Moderator/Admin | Download full dataset as CSV for detailed review. Allows moderators to check data quality before approval. | Simple |  |  | Done | GET /api/moderation/{id}/download returns full CSV
28 | Approve Dataset | Moderation | Moderator/Admin | Approve dataset after quality check. Changes status to Approved, makes dataset visible in marketplace. Creates moderation history record. | Simple |  |  | Done | PUT /api/moderation/{id}/approve with status update
29 | Reject Dataset | Moderation | Moderator/Admin | Reject dataset with reason. Changes status to Rejected, notifies provider. Requires rejection reason. Creates moderation history record. | Simple |  |  | Done | PUT /api/moderation/{id}/reject with reason validation
30 | Admin Dashboard | System Monitoring | Admin | System dashboard showing: total revenue, user counts by role, dataset statistics, recent activities, system health metrics. | Medium |  |  | Done | Dashboard with aggregated statistics from multiple sources
31 | System Pricing Management | System Monitoring | Admin | Manage pricing configuration for 3 package types. Set price per unit (row/call/month) and commission percentages (provider/admin split). | Medium |  |  | Done | CRUD operations for SystemPricing: GET/PUT /api/pricing/{id}
32 | Revenue Summary | Revenue | Admin | View revenue summary by month. Shows total revenue, provider shares, admin commission, pending payouts. Filter by month/year. | Medium |  |  | Done | GET /api/payouts with month filtering and revenue aggregation
33 | Process Payout | Revenue | Admin | Generate monthly payout for providers. Calculates pending revenue shares, creates payout records. Requires transaction reference for completion. | Complex |  |  | Done | POST /api/payouts/process with revenue calculation and payout generation
34 | Payout History | Revenue | Admin | View payout history showing completed and pending payouts. Filter by provider, month, status. Shows transaction references. | Medium |  |  | Done | Payout list with filtering and status tracking
35 | Provider Earnings View | Revenue | Data Provider | Providers can view their earnings summary, revenue shares by month, pending payouts, payout history. Shows contribution percentages. | Medium |  |  | Done | GET /api/payouts/provider/earnings with provider-specific filtering
36 | Province Selection | Location Management | All Users | Dropdown/select component for 63 Vietnamese provinces. Used in dataset upload, purchase filters, location-based queries. | Simple |  |  | Done | GET /api/locations/provinces returns all provinces
37 | District Selection | Location Management | All Users | Dropdown/select component for 62 districts (Hanoi: 30, HCMC: 24, Danang: 8). Used for granular location filtering. | Simple |  |  | Done | GET /api/locations/districts?provinceId=X returns districts for province
38 | Error Handling | System Monitoring | All Users | Global error handling with user-friendly error messages. 401 auto-logout, 404 not found, 500 server errors. Error boundaries in React. | Medium |  |  | Done | Error handling middleware, error boundaries, user-friendly messages
39 | Loading States | User Experience | All Users | Loading spinners and skeleton screens during API calls. Prevents UI freezing, improves user experience. | Simple |  |  | Done | Loading states in all components with Spinner component
40 | Responsive Design | User Experience | All Users | Responsive design for mobile, tablet, desktop. TailwindCSS breakpoints, mobile-friendly navigation, adaptive layouts. | Medium |  |  | Done | TailwindCSS responsive utilities, mobile-first design
41 | Role-Based Layouts | User Experience | All Users | Different layouts for each role: ConsumerLayout (header+footer), ProviderLayout (sidebar), AdminLayout (sidebar), ModeratorLayout (sidebar). | Medium |  |  | Done | SmartLayout component auto-selects layout based on user role
42 | Protected Routes | Authentication & Authorization | All Users | Route protection based on user roles. Redirects unauthorized users, shows 403 for forbidden pages. | Medium |  |  | Done | Route guards with role checking, redirect logic